## Slide 1
COUNCIL DRAFT • DECISION FIRST
From chasing spreadsheets
to delivering warmer homes
01 / PROPER WARM • REQUEST + PROPOSAL • E01/E02/E07 • 11 Oct 2026
Offer: one staff retrofit workbench linking cases, owners and evidence.
Today: endorse preparation of its gated evidence-stage proposal.
ONE PROGRAMME
ONE EVIDENCE TRAIL
HUMAN CONTROL
Evidence
Choice
Handover
Notes: Proper Warm began with a request to coordinate a complex retrofit programme across sixty thousand homes using five agents. The offer is one staff-facing workbench linking cases, accountable owners and evidence through to accepted handover. Our ambition is warmer homes with a clear next step for every home, not faster administration alone.
Today I am asking the council to endorse preparation of a gated evidence-stage proposal, not a production rollout or accelerated capital commitment. For the CEO, that is confidence in the mission. For Assets, it is a defensible route to accepted handover. For Finance, it is visibility of commitments, exposure and evidence before money moves. The promise is one programme, one evidence trail, human control. The measurable benefits still have to be earned.
Evidence:
docs/case_study_48_original.md — Business Challenge; Agentic Architecture Brief; Expected Outcomes (2026-09-10, immutable request)
docs/case_study_48_addendum.md — Business Challenge; Regulatory Evidence and Service Design; Proper Warm at Proper North Homes (2026-10-11, maintained proposal)
docs/case_study_48_addendum.md — Subsequent Application Exercise Builds (2026-10-11); Current Learning and Parallel Experiment (owner direction; feasibility not benefit)
docs/reference/research/company/company-profile-research.md — Confirmed Company Information; Modelled Customer Profile; Role and Decision Map (2026-09-26; not-for-profit owner-confirmed, other attributes modelled)

## Slide 2
WHAT WE FOUND
Research changed the question
02 / PROPER WARM • RESEARCH HYPOTHESES • E02/E03/E04 • 26–27 Sep 2026
THE CONSTRAINT
Capital, capacity, access and quality may bind—not just administration.
THE FOUNDATION
Shared records, clear lifecycle states and accountable handoffs.
THE AI OPPORTUNITY
Read, reconcile, draft and flag—inside the controls.
Better inputs do not confer authority. Faster activity is not accepted handover.
Notes: The original question was which agents to build. The research asked what actually prevents safe, accepted completions. Spreadsheet dependence is in the case, but it is not proof that administration is the binding constraint. Capital, competent assessors, supplier capacity, access, evidence quality and downstream assurance may matter more.
The role challenge found that every end-to-end agent request mixed deterministic controls, accountable decisions and narrower AI tasks. Richer photos, invoices and sensor inputs did not change that division. Better inputs cannot create consent or professional acceptance.
Our conclusion is to build a shared coordination and evidence foundation, then add assistance where comparative tests show net benefit. The regulatory material is a dated research set. The current register distinguishes final energy policy from proof of a commenced landlord duty. We have not refreshed legal currentness for this pitch.
Evidence:
docs/case_study_48_addendum.md — Business Challenge; Regulatory Evidence and Service Design; Proper Warm at Proper North Homes (2026-10-11, maintained proposal)
docs/reference/research/company/agent-request-challenge.md — Purpose and Method; Summary (2026-09-26, role-agent hypotheses)
docs/reference/research/company/agent-what-if-study.md — Purpose and Method; Summary of Revised Verdicts (2026-09-27, role-agent hypotheses)
docs/reference/research/company/company-profile-research.md — Confirmed Company Information; Modelled Customer Profile; Role and Decision Map (2026-09-26; not-for-profit owner-confirmed, other attributes modelled)

## Slide 3
WHO WE ASKED
We challenged the gaps—not just the technology
03 / PROPER WARM • ROLE AGENTS ≠ STAFF INTERVIEWS OR APPROVALS • E03/E05/E06/E12
ASSETS + FINANCE
Investment authority • gross cash • attributable value
PROGRAMME + PROCUREMENT
Capacity • professional review • supplier accountability
RESIDENTS + FRONTLINE
Choice • safe contact • accepted handoffs
SAFETY + DATA
Hazard route • missingness • independent evaluation
Notes: Eight documented role agents challenged the request: Assets, Programme, Finance, Procurement, Resident Engagement, Building Safety, Data and Performance, and the Neighbourhood Housing Officer. Each brought a different failure question. Who approves the investment? Who accepts quality? Who owns a pending handoff? What happens when a resident cannot use a digital channel? Does faster activity simply move the queue elsewhere?
These were research instruments using sector-informed hypotheses, not employee interviews or corporate approval. The measurement challenge forced us to separate programme change from AI contribution.
Later, Programme, Finance, Resident Engagement and Data instruments proposed reconciled exercise assumptions. The project owner accepted the v0.12 baseline on 10 October. Owner UX feedback separately asked for visible readiness, ownership and agent purpose. None of that substitutes for direct staff or resident validation, or acceptance of the current candidate.
Evidence:
docs/reference/research/company/agent-request-challenge.md — Purpose and Method; Summary (2026-09-26, role-agent hypotheses)
docs/reference/research/company/pilot-measurement-challenge.md — Summary; Owner Decision, 2026-09-26; Proposed Measurement Design (2026-09-26, proposed comparisons)
docs/case_study_48_addendum.md — Owner-Approved Exercise Baseline (2026-10-10); EXA-001/002/004/005/008/010/011/012/013/015/016; Numerical Targets and Attribution (historical accepted exercise assumptions)
docs/reference/research/ux/proper-warm-prototype-profile-review.md — Owner Usability Feedback (2026-10-07); Proposed Acceptance Checks UX-01 to UX-08 (reported impressions, unexecuted checks)

## Slide 4
ARCHITECTURE DECISIONS
One retrofit workbench. Not five autonomous agents.
04 / PROPER WARM • OWNER DIRECTION + PROPOSED DESIGN • E07–E10 • 11 Oct 2026
THE PRODUCT
Staff workbench + role queues
One linked home / work package
Evidence, handoffs, quality + finance
BOUNDED ASSISTANCE
Deterministic priority + workflow
AI drafts / selects / flags
People accept, decide and act
CUSTOMER OUTCOME
See owner, next action + blocker
Track capacity to accepted handover
Measure effort, quality + cost
Reuse data and API contracts. Prove controls. Platform choice is not company approval.
Notes: We are proposing one staff-facing retrofit workbench: linked home, building, scheme, work package and service cases, with role queues over shared status, evidence, owners, blockers, capacity and finance. It coordinates work; it does not replace every source system or create five autonomous agents.
Deterministic rules control ranking and transitions. Bounded AI drafts, selects or flags; people decide. Azure SQL, Blob and a controlled API are the exercise direction. The customer benefit to test is one accountable case and next action through accepted handover. Time, rework and completion improvement are not yet measured.
Actual Azure, SQL and AI are required in subsequent accepted exercise deliveries. This is not a production platform selection: Excel-only and M365 options still need comparable appraisal.
Evidence:
docs/reference/research/company/agent-request-challenge.md — Purpose and Method; Summary (2026-09-26, role-agent hypotheses)
docs/case_study_48_addendum.md — Subsequent Application Exercise Builds (2026-10-11); Current Learning and Parallel Experiment (owner direction; feasibility not benefit)
docs/prds/proper-warm-retrofit-programme-demonstrator.md — front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11; historical v0.12.0 accepted 2026-10-10)
docs/adrs/0001-azure-architecture.md — Exercise Applicability (2026-10-11); Decisions; Hybrid M365 and Excel transition; Options still to compare (proposed)
docs/adrs/0002-pilot-readiness-architecture.md — Exercise Applicability (2026-10-11); Decisions; 1. Durable store (proposed readiness design)

## Slide 5
WHAT WE BUILD • SYSTEM LANDSCAPE • PROPOSED, NOT DEPLOYED
One workbench, one shared case, every role
05 / PROPER WARM • TARGET LANDSCAPE • PROPOSED DESIGN • E07/E08/E09
WHO USES IT
WHERE THE FACTS COME FROM
WHAT WE ARE BUILDING
Programme + retrofit coordinators
Excel workbooks
(validated one-way import)
Surveyors, assessors + installers
Housing, asset + stock data
Residents + contractors
(controlled touchpoints)
Surveys, photos + evidence
Finance, quality + managers
Funding + grant rules
PROPER WARM RETROFIT WORKBENCH
One case per home or work package
Owner, next action, blocker
Evidence, approvals, audit
Bounded AI drafts; people decide
Notes: This is the whole product on one page. On the left are the people who touch a retrofit: coordinators, surveyors and installers, finance and quality managers, and residents and contractors through controlled touchpoints. On the right is where the facts come from today: Excel workbooks, housing and stock data, surveys and evidence, and funding rules.
In the middle is what we build: one workbench with one linked case per home or work package. Everyone sees the same owner, next action and blocker, and the evidence behind a decision.
It sits beside existing sources and reuses their data through a validated one-way import. It does not replace every system, and it does not give residents or contractors open access. Speed and experience gains are mechanisms to test, not measured results.
Evidence:
docs/prds/proper-warm-retrofit-programme-demonstrator.md - front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11)
docs/adrs/0001-azure-architecture.md - Exercise Applicability (2026-10-11); Decisions; Hybrid M365 and Excel transition (proposed)
docs/adrs/0002-pilot-readiness-architecture.md - Exercise Applicability (2026-10-11); Decisions (proposed readiness design)

## Slide 6
PROPOSED CONTROL FLOW • CONCEPTUAL, NOT DEPLOYED
One controlled route from evidence to action
06 / PROPER WARM • TARGET CONTROL DESIGN—NOT A DEPLOYED TOPOLOGY • E08/E09/E10
WORKBOOK + SOURCE DATA
Validated one-way import
CONTROLLED API
Identity • access • approvals
SHARED CASE + EVIDENCE
Azure SQL + versioned Blob
STAFF WORKBENCH
Read case • request gated action
Human review before change
WORKFLOW RULES
Own • route • check • audit
BOUNDED AI • NO WRITE
Permitted inputs
Cited draft / flag to staff
Notes: This is one product with a controlled flow. Workbooks enter through validated, one-way import. Staff read a shared case and request actions through role-specific workbench views; the API checks identity, case access, evidence versions and required approvals before SQL state changes. Deterministic workflow routes tasks and gates.
Bounded AI receives permitted inputs and can return a typed choice, cited draft or concern to staff. It has no write credentials and cannot advance a case. A person reviews before any controlled change, then acts through the API. If AI fails, staff use the manual route without bypassing controls. Conflicting identifiers are quarantined, not silently merged.
This is a target design, not a deployed topology. Production identity, workload separation, private access, monitoring and recovery need separate proof. Narrow AI/SQL feasibility does not verify every component shown.
Evidence:
docs/prds/proper-warm-retrofit-programme-demonstrator.md — front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11; historical v0.12.0 accepted 2026-10-10)
docs/adrs/0001-azure-architecture.md — Exercise Applicability (2026-10-11); Decisions; Hybrid M365 and Excel transition; Options still to compare (proposed)
docs/adrs/0002-pilot-readiness-architecture.md — Exercise Applicability (2026-10-11); Decisions; 1. Durable store (proposed readiness design)
docs/ideas/typesafe-system-one-agent-fit.md — Observed Feasibility and Parallel Value Experiment (2026-10-11); Microsoft Decision 1 Reassessment (2026-10-10). PR #58 pinned 5136f192d583a5bf53adeeec4b0f21369b005c9d; inspected in maintained documentation 2026-10-11, not runtime reverified

## Slide 7
WHAT WE BUILD • LAYERED ARCHITECTURE • PROPOSED, NOT DEPLOYED
Four layers keep speed, control and AI separate
07 / PROPER WARM • TARGET LAYERS • PROPOSED DESIGN, PROOF STILL REQUIRED • E08/E09/E10
1 EXPERIENCE
Role queues, case view and controlled resident touchpoints
2 WORKFLOW + RULES
Deterministic ranking, routing, gates and blockers
3 CONTROLLED API
Identity, case-level access, approvals and audit
4 CASE + EVIDENCE
Azure SQL case state, versioned Blob evidence, Excel import
BOUNDED AI
Permitted inputs only; cited draft or flag; no write credentials
ACROSS ALL LAYERS: least privilege, monitoring, recovery and human approval, each still to be proven
Notes: Here is the same system as layers. Staff and, later, controlled resident touchpoints use role queues and one case view. Beneath that, deterministic workflow rules rank work, route tasks and hold gates, so priority is explainable rather than a model's guess.
Every action passes the controlled API, which checks identity, case-level access, evidence versions and approvals before the case store changes. Case state sits in Azure SQL, evidence in versioned Blob storage, and Excel arrives by validated one-way import.
Bounded AI sits to the side. It receives permitted inputs and returns a cited draft, a typed choice or a flag to a person. It has no write credentials, so it can make staff faster without being able to act alone.
The bottom band is what we still have to prove: least privilege, monitoring, recovery and approval. This is a target design, not a deployed topology.
Evidence:
docs/prds/proper-warm-retrofit-programme-demonstrator.md - front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11)
docs/adrs/0001-azure-architecture.md - Exercise Applicability (2026-10-11); Decisions; Hybrid M365 and Excel transition (proposed)
docs/adrs/0002-pilot-readiness-architecture.md - Exercise Applicability (2026-10-11); Decisions (proposed readiness design)

## Slide 8
WHAT CHANGES FOR USERS • EXPERIENCE AND SPEED • HYPOTHESES TO TEST
Same case, fewer chases: a working day
08 / PROPER WARM • SECTOR-INFORMED HYPOTHESES • NO TIME SAVED IS YET MEASURED • E05/E09/E12
TODAY: WORKBOOKS AND CHASING (HYPOTHESIS)
WITH THE WORKBENCH (MECHANISM TO TEST)
Search workbooks and inboxes for the case
Open one linked case with owner and blocker
Ask colleagues what happens next
See a ranked next action in your queue
Hunt for the latest file to prove a decision
Evidence and approvals attached to the case
Rewrite status updates by hand
Cited draft for staff to check and send
Notes: Take one working day for a coordinator. Today, in a workbook-led process, finding a case can mean searching several workbooks and inboxes. Knowing what happens next can mean asking a colleague. Proving a decision can mean hunting for the latest file, and updating a resident or contractor can mean rewriting the same status by hand. These are sector-informed hypotheses about Excel, not findings about Proper North Homes.
With the workbench, the same person opens one linked case that shows the owner and blocker, sees a ranked next action, finds evidence and approvals attached, and reviews a cited draft update before sending it.
Speed comes from fewer searches, fewer chases and fewer retyped updates. We will test it by timing find-the-case, chase counts and rework in a paired exercise against the current route. No time saving is measured yet, and residents and contractors benefit through clearer, more consistent updates that staff still approve.
Evidence:
docs/reference/research/company/agent-request-challenge.md - Purpose and Method; Summary (2026-09-26, role-agent hypotheses)
docs/case_study_48_addendum.md - Subsequent Application Exercise Builds (2026-10-11); Current Learning and Parallel Experiment (feasibility, not benefit)
docs/prds/proper-warm-retrofit-programme-demonstrator.md - Executive Summary; paired proof criteria (v0.13.0 candidate 2026-10-11)

## Slide 9
MECHANISM BEFORE MARKETING
Excel stays useful. It stops being the control system.
09 / PROPER WARM • PROPOSED SUPERIORITY—PAIRED PROOF STILL REQUIRED • E05/E09/E12
START WITH THE WORKBOOK
Case fact: spreadsheets coordinate work
Measure current effort, errors and rework
Failure modes remain hypotheses
SAFE, SUPPORTED CHANGE
Shadow import → reconcile
Short parallel run → clear exit tests
Workbench writes; Excel read-only
CASE FACT: spreadsheets coordinate work. PROPOSED: linked case + named owner + checked handoff. Better by how much? Not measured.
Notes: The case says spreadsheets coordinate the work; it does not prove repeated reconciliation or evidence reassembly. Measure before claiming staff pain, saved time or fewer errors.
The proposed improvement mechanism is one linked case, named handoff owner and independently checked transition. How much better it is remains unknown until equal tasks are compared for effort, errors, rework and accepted outcomes. Do not claim Excel cannot be hardened.
Manage change in stages: co-design with staff, profile workbook owners, then shadow one-way imports. Run a short, time-boxed parallel period with named editors, quarantine ownership and owner-agreed reconciliation and exit thresholds. Train through role-based task walkthroughs and provide named support. After sign-off, tested rollback and an out-of-hours hazard route, the workbench becomes the write path and Excel an API-fed read-only report. No permanent dual write.
Compare identical tasks and outcomes, including review, correction, chase, errors and accepted handovers. Tenant, workbook quality, staff readiness and results remain unknown.
Evidence:
docs/case_study_48_original.md — Business Challenge; Agentic Architecture Brief; Expected Outcomes (2026-09-10, immutable request)
docs/reference/research/company/pilot-measurement-challenge.md — Summary; Owner Decision, 2026-09-26; Proposed Measurement Design (2026-09-26, proposed comparisons)
docs/adrs/0001-azure-architecture.md — Exercise Applicability (2026-10-11); Decisions; Hybrid M365 and Excel transition; Options still to compare (proposed); see appendix slide 21 for the unscored comparison
docs/reference/research/ux/proper-warm-prototype-profile-review.md — Owner Usability Feedback (2026-10-07); Proposed Acceptance Checks UX-01 to UX-08 (reported impressions, unexecuted checks)

## Slide 10
THE CONNECTED OPERATING JOURNEY
Connect every handoff from intake to accepted home
10 / PROPER WARM • EXERCISE JOURNEY + INDEPENDENT GATES • E06/E08 • NOT LIVE WORK
INTAKE + RANK
Resolve home • approved rules
ASSESS + AGREE
Survey • design • resident choice
RESOURCE + DELIVER
Funding • crew capacity • work
VERIFY + CLOSE
Independent QA • handover • finance
Closed loop: defects / changed evidence → owned re-review • accepted handover • separate finance close
Notes: The workbench coordinates the full journey: identify and prioritise the home; assess technical scope and resident choice; confirm funding, competent capacity and human release; then deliver, verify quality, resolve defects, hand over to the resident and close finance with separate evidence.
Staff can see owner, blocker, next action and returned work across handoffs. A sent task is not an accepted task. The intended outcome is accepted handover, not starts. This is a control mechanism to evaluate on constructed records, not evidence that real work or improvement has occurred.
Evidence:
docs/case_study_48_addendum.md — Owner-Approved Exercise Baseline (2026-10-10); EXA-001/002/004/005/008/010/011/012/013/015/016; Numerical Targets and Attribution (historical accepted exercise assumptions)
docs/prds/proper-warm-retrofit-programme-demonstrator.md — front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11; historical v0.12.0 accepted 2026-10-10)
docs/reference/research/ux/proper-warm-prototype-profile-review.md — Owner Usability Feedback (2026-10-07); Proposed Acceptance Checks UX-01 to UX-08 (reported impressions, unexecuted checks)

## Slide 11
RESIDENT VALUE • DIGNITY BY DESIGN
Give staff, residents and contractors a clear next step
11 / PROPER WARM • PROPOSED SERVICE + OWNER-REPORTED UX • E06/E12 • VALIDATION PENDING
RESIDENT
CHOICE
STAFF • INTERNAL WORKBENCH
Owner • blocker • evidence • next action
RESIDENTS • NO REQUIRED PORTAL
Supported contact • options • human help
CONTRACTORS • APPROVED CHANNEL
Scope • schedule • minimum-necessary information
Notes: Staff work from role queues showing owner, blocker, evidence and next action. Residents get clear choices, a named contact and safe phone, letter, text, email or officer-assisted routes; no mandatory portal. Contact preference, adjustment and measure consent are separate. Silence is not consent, and hazards reach a human response route outside routine scheduling.
Contractors receive the agreed scope, schedule and necessary adjustments through approved channels, then return completion evidence. Neither residents nor contractors are assumed to log in to the staff tool; sensitive diagnoses are not shared. These handoffs may improve clarity, but fewer visits, delays or defects are unproved. Accessible staff, resident and contractor co-design/testing remain prerequisites.
Evidence:
docs/case_study_48_addendum.md — Owner-Approved Exercise Baseline (2026-10-10); EXA-001/002/004/005/008/010/011/012/013/015/016; Numerical Targets and Attribution (historical accepted exercise assumptions)
docs/reference/research/ux/proper-warm-prototype-profile-review.md — Owner Usability Feedback (2026-10-07); Proposed Acceptance Checks UX-01 to UX-08 (reported impressions, unexecuted checks)
docs/reference/research/company/company-profile-research.md — Confirmed Company Information; Modelled Customer Profile; Role and Decision Map (2026-09-26; not-for-profit owner-confirmed, other attributes modelled)

## Slide 12
TWO CAPABILITIES • ONE AUTHORITY BOUNDARY
AI prepares the decision. People own it.
12 / PROPER WARM • REAL FEASIBILITY ≠ TASK BENEFIT • E07/E11 • 11 Oct 2026
TYPED SCORING
Decision 1
Supplied candidates and bounded checks
Explicit no-match / uncertainty
Placement conditional on verified task fit
CITED GENERATION
Foundry generative model
Draft narrative from permitted sources
Review every required field
No invented facts or submission
NEVER AI-OWNED: priority policy • compliance • consent • technical approval • claims • QA • payment
Notes: We distinguish typed scoring from text generation. Decision 1 can select from supplied, source-bound candidates or support a bounded evidence check only when its actual task fit is verified. It should expose no-match or uncertainty rather than invent a missing value. A real Foundry generative task can assemble a cited narrative from approved inputs. That narrative is still a draft.
Neither capability owns priority policy, regulatory satisfaction, consent, technical approval, grant submission, quality acceptance or payment. The API enforces that boundary. Individual manual access does not waive required real AI in an application delivery.
Documented feasibility includes source-bound EPC selection and cited generation. Benefit, calibration and broader screening remain unproved. The binary adapter cannot establish a three-class screening score. The parallel experiment is not completed evidence.
Evidence:
docs/reference/research/company/agent-request-challenge.md — Purpose and Method; Summary (2026-09-26, role-agent hypotheses)
docs/case_study_48_addendum.md — Subsequent Application Exercise Builds (2026-10-11); Current Learning and Parallel Experiment (owner direction; feasibility not benefit)
docs/prds/proper-warm-retrofit-programme-demonstrator.md — front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11; historical v0.12.0 accepted 2026-10-10)
docs/ideas/typesafe-system-one-agent-fit.md — Observed Feasibility and Parallel Value Experiment (2026-10-11); Microsoft Decision 1 Reassessment (2026-10-10). PR #58 pinned 5136f192d583a5bf53adeeec4b0f21369b005c9d; inspected in maintained documentation 2026-10-11, not runtime reverified

## Slide 13
SECURITY POSTURE • PROPOSED CONTROLS, ASSURANCE OPEN
Prove security. Cloud hosting is not proof.
13 / PROPER WARM • PINNED #58 DOCUMENTED FEASIBILITY • E07/E08/E11 • 11 Oct 2026
DATA + ACCESS
Role / case / field checks
Minimum-necessary inputs
Constructed data only for exercise
CONTROL BOUNDARY
API is the only write route
AI cannot write or approve
Independent human gates
PROOF REQUIRED
Authorization / leakage tests
Recovery / audit verification
Security + privacy approval
Design controls are not a security certification • No personal data or live decisions in this exercise
Notes: Cloud alone does not make this secure. Proposed controls are server-enforced role/case/field rights, minimum-necessary model inputs, one API write path, independent human gates, versioned evidence and audit. The AI identity cannot write programme state. The exercise uses constructed, non-identifying records.
No penetration, authorization, cross-case leakage, recovery or privacy assessment is claimed. Verify controls against the actual deployment before real data or operations. Narrow Azure SQL/Blob/AI feasibility does not certify the target design. The continuing sixty-thousand-home stock and nine-hundred-and-eighty-case programme are generated; v0.13 remains pending fresh review and owner acceptance.
Evidence:
docs/case_study_48_addendum.md — Subsequent Application Exercise Builds (2026-10-11); Current Learning and Parallel Experiment (owner direction; feasibility not benefit)
docs/prds/proper-warm-retrofit-programme-demonstrator.md — front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11; historical v0.12.0 accepted 2026-10-10)
docs/adrs/0002-pilot-readiness-architecture.md — Exercise Applicability (2026-10-11); Decisions; 1. Durable store (proposed readiness design)
docs/ideas/typesafe-system-one-agent-fit.md — Observed Feasibility and Parallel Value Experiment (2026-10-11); Microsoft Decision 1 Reassessment (2026-10-10). PR #58 pinned 5136f192d583a5bf53adeeec4b0f21369b005c9d; inspected in maintained documentation 2026-10-11, not runtime reverified

## Slide 14
RETROFIT CASH EXAMPLE • FICTIONAL, NOT WORKBENCH PRICE OR BUDGET
The CFO test: cash exposure before grant optimism
14 / PROPER WARM • FICTIONAL EXA-010/015 ARITHMETIC • E06 • ACCEPTED EXERCISE 10 Oct 2026
£20,000
gross base cash exposure
£7,500
fictional grant—not cash yet
£12,500
provider base funding
IF CONTINGENCY SPENT £22,000 gross envelope / £14,500 provider exposure
Application ≠ award ≠ claim ≠ cash. Actual terms, liquidity and delegated authority remain unknown.
Notes: This fictional fixture shows why Finance sees gross cash, not an assumed grant offset: GBP20,000 base cost, GBP7,500 illustrative grant and GBP12,500 provider base funding. If contingency is spent, the gross envelope is GBP22,000 and provider exposure GBP14,500. Before grant cash arrives, exposure is still GBP20,000.
These are exercise assumptions, not company budget, award terms or liquidity. Technology requires its own authority and stop conditions. Technology whole-life cost remains unassessed and belongs in the return pack. Measure effort and cost per accepted outcome before treating time saved as cashable benefit.
Evidence:
docs/case_study_48_addendum.md — Owner-Approved Exercise Baseline (2026-10-10); EXA-001/002/004/005/008/010/011/012/013/015/016; Numerical Targets and Attribution (historical accepted exercise assumptions)
docs/case_study_48_addendum.md — Subsequent Application Exercise Builds (2026-10-11); Current Learning and Parallel Experiment (owner direction; feasibility not benefit)
docs/reference/research/company/company-profile-research.md — Confirmed Company Information; Modelled Customer Profile; Role and Decision Map (2026-09-26; not-for-profit owner-confirmed, other attributes modelled)

## Slide 15
MEASUREMENT, NOT A SUCCESS DASHBOARD
Prove the transformation; test whether AI adds value
15 / PROPER WARM • PROPOSED COMPARISONS • E05/E11 • NO RESULTS CLAIMED
COMPARISON 1 • PROGRAMME
Existing teams / matched localities
Same event capture and frozen cohort
Accepted handovers + whole-chain cost
Log shared resources and displacement
COMPARISON 2 • CAPABILITY
Paired manual/rules versus assistance
Same inputs and reviewed outcomes
Full review effort + errors + latency + cost
Parallel experiment: no results yet
Guardrails: safety • resident choice • quality • equity • peak cash. Include unfinished and withdrawn cases.
Notes: Separate two tests: does the coordinated programme improve safe accepted handovers, and does a specific AI task outperform the same workflow without it? Compare matched localities for programme outcomes and paired, identical tasks for capability value. Include incomplete, paused and withdrawn cases, shared resources and displacement. Measure errors, review effort, delay, cost and uncertainty; protect safety, consent, equity and quality.
These are proposed comparisons, not results. A negative AI finding means retain the simpler path and report it.
Evidence:
docs/reference/research/company/pilot-measurement-challenge.md — Summary; Owner Decision, 2026-09-26; Proposed Measurement Design (2026-09-26, proposed comparisons)
docs/case_study_48_addendum.md — Owner-Approved Exercise Baseline (2026-10-10); EXA-001/002/004/005/008/010/011/012/013/015/016; Numerical Targets and Attribution (historical accepted exercise assumptions)
docs/ideas/typesafe-system-one-agent-fit.md — Observed Feasibility and Parallel Value Experiment (2026-10-11); Microsoft Decision 1 Reassessment (2026-10-10). PR #58 pinned 5136f192d583a5bf53adeeec4b0f21369b005c9d; inspected in maintained documentation 2026-10-11, not runtime reverified

## Slide 16
PLANNING ONLY • PROPOSED GATES
Prepare the evidence stage in four decision gates
16 / PROPER WARM • PROPOSED NEXT STAGE • E06–E10 • SCOPE/BUDGET/ACCEPTANCE REQUIRED
1 • ACCEPT
Freshly reviewed requirements + named owners + defined authority
2 • CONNECT
Real Azure/SQL/AI + continuing lineage + negative controls
3 • PROVE
Paired task value + engineering/accessibility/recovery evidence
4 • DECIDE
Owner evidence review: continue / simplify / stop
Notes: Gate the next stage around decisions, not service counts. First review and accept the current requirements candidate, name accountable owners, freeze the evidence and test contracts, and record effective scope and spending authority. No missing approval is solved by running another model.
Prove connected case controls on continuing generated data using actual Azure, SQL and registered inference. Show version-linked write, read and restart evidence, independent decisions and negative permission tests. Unit-test mocks cannot establish delivered application acceptance.
Then evaluate net task value and engineering readiness, including accessibility, recovery, performance and accrued costs. Finally return a reviewable evidence pack to the owner with pass, fail, blocked and not-run states. The earlier four-week exercise plan was a software delivery scenario, not a physical retrofit programme or unconditional timetable for this candidate. Only subsequent operational appraisal, real user research and formal control-owner approval could justify a live pilot.
Evidence:
docs/case_study_48_addendum.md — Owner-Approved Exercise Baseline (2026-10-10); EXA-001/002/004/005/008/010/011/012/013/015/016; Numerical Targets and Attribution (historical accepted exercise assumptions)
docs/case_study_48_addendum.md — Subsequent Application Exercise Builds (2026-10-11); Current Learning and Parallel Experiment (owner direction; feasibility not benefit)
docs/prds/proper-warm-retrofit-programme-demonstrator.md — front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11; historical v0.12.0 accepted 2026-10-10)
docs/adrs/0001-azure-architecture.md — Exercise Applicability (2026-10-11); Decisions; Hybrid M365 and Excel transition; Options still to compare (proposed)
docs/adrs/0002-pilot-readiness-architecture.md — Exercise Applicability (2026-10-11); Decisions; 1. Durable store (proposed readiness design)

## Slide 17
COUNCIL DECISION • ENDORSE PLANNING ONLY
Endorse the evidence stage—not delivery spend or production.
17 / PROPER WARM • DRAFT FOR CHALLENGE • E07/E08/E16 • NO PRODUCTION OR SPEND APPROVAL
CEO
Nominate an executive sponsor
Require an evidence-led return
ASSETS CxO
Nominate workflow / control owners
Confirm non-negotiable gates
CFO
Define the affordability review
Define authority review + stop tests
Return: reviewed requirements • options • cost / authority • acceptance / stop tests • date to agree
Notes: The decision requested today is limited: endorse preparation of a gated evidence-stage proposal. It does not authorize procurement, deployment, delivery spend or production adoption. Ask the CEO to nominate an executive sponsor, Assets to nominate workflow and control owners, and Finance to define how affordability and authority will be reviewed. Confirm the actual delegated roles rather than assuming them.
Return at a date the council agrees with freshly reviewed requirements, an unscored comparable options appraisal, scoped cost and authority, acceptance evidence and explicit stop conditions. The evidence must show whether the connected workflow works, whether assistance earns its cost, and which gates remain unmet. If value is absent, simplify. If controls fail, stop and repair.
Our ambition remains bold: move from chasing spreadsheets to warmer homes through one programme, one evidence trail and human control. The case is accountable handovers, not AI theatre.
Evidence:
docs/reference/research/company/pilot-measurement-challenge.md — Summary; Owner Decision, 2026-09-26; Proposed Measurement Design (2026-09-26, proposed comparisons)
docs/case_study_48_addendum.md — Subsequent Application Exercise Builds (2026-10-11); Current Learning and Parallel Experiment (owner direction; feasibility not benefit)
docs/prds/proper-warm-retrofit-programme-demonstrator.md — front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11; historical v0.12.0 accepted 2026-10-10)
docs/reference/method/ama-capstone-assessment-guide.md — Sections A-D; How the outcome is determined; How to prepare (2026-09-30 published rubric)

## Slide 18
APPENDIX A • TARGET DESIGN, NOT DEPLOYMENT CLAIM
Technical Q&A: isolate failure, preserve control
18 / PROPER WARM • PROPOSED PATTERNS + OPEN ASSURANCE • E08/E09/E10/E11
STATE & SCALE
SQL row versions / idempotency
Indexed queries / paging
Blob evidence versions
Restart and restore tests
TRUST BOUNDARIES
Role / case / field rights
Permitted model inputs
Schema / source validation
No agent decision writes
FAILURE & OPERATIONS
Manual route on AI failure
Unknown facts hold reviews
Audit / cost telemetry
Recovery still to prove
Notes: Threats include unauthorized writes, stale approvals, cross-case leakage, malicious content in evidence, model hallucination and lost or competing state. Proposed controls are one API write path, server-side role/case/field projections, source-bound inputs, schema validation, independent reviewers, row-version concurrency, idempotent transitions and replayable audit.
SQL indexes and server-side paging/clustering address full-file and full-map mechanisms. Queue-separated workers and private-only access remain proposed topology, not deployed facts. Model failure retains manual work; unsupported source facts stay unknown; retries must not duplicate transitions. Blob versions and SQL metadata must identify exactly which evidence was approved. Recovery, ledger verification, replicas, user identity, leakage/injection tests and legal retention decisions need explicit observed evidence before readiness claims.
Evidence:
docs/prds/proper-warm-retrofit-programme-demonstrator.md — front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11; historical v0.12.0 accepted 2026-10-10)
docs/adrs/0001-azure-architecture.md — Exercise Applicability (2026-10-11); Decisions; Hybrid M365 and Excel transition; Options still to compare (proposed)
docs/adrs/0002-pilot-readiness-architecture.md — Exercise Applicability (2026-10-11); Decisions; 1. Durable store (proposed readiness design)
docs/ideas/typesafe-system-one-agent-fit.md — Observed Feasibility and Parallel Value Experiment (2026-10-11); Microsoft Decision 1 Reassessment (2026-10-10). PR #58 pinned 5136f192d583a5bf53adeeec4b0f21369b005c9d; inspected in maintained documentation 2026-10-11, not runtime reverified

## Slide 19
APPENDIX B • ANSWERS WITH REVERSAL CONDITIONS
Council Q&A: the objections we welcome
19 / PROPER WARM • ALTERNATIVES, AFFORDABILITY, AUTHORITY • E05/E07/E09/E11
WHY NOT EXCEL / M365?
Cost equivalent options; control mechanisms must win.
WHY NOT LAUNCH NOW?
Feasibility is not full workflow or human acceptance.
WHAT BUDGET?
New scoped authority needed; prior cap/override is historical.
WHAT IF AI FAILS?
Keep manual work; simplify failed tasks; preserve gates.
Notes: Why not fix Excel? We should cost that option; the proposed control mechanisms, not familiarity alone, decide the comparison. Why not Power Platform? Tenant/licensing and operational fit are unverified and require equivalent appraisal before production selection. Why buy AI now? Do not buy an assumed benefit; verify access, terms and scoped authority, then run paired task tests. Why not launch from #58? Narrow observed feasibility is not full workflow/control or human acceptance.
What is the budget? No new corporate amount is approved. Historical EXA-012 allocated USD450 per month, reviewed at USD360 and paused at USD405; #58 removed that cap only for its rebuild. Each subsequent build needs an effective scoped approval with accrued liabilities. Stop if controls fail, authority is absent or liabilities exceed the agreed envelope. Simplify any AI task that fails net-value testing; keep required real-platform evidence independent.
Evidence:
docs/reference/research/company/pilot-measurement-challenge.md — Summary; Owner Decision, 2026-09-26; Proposed Measurement Design (2026-09-26, proposed comparisons)
docs/case_study_48_addendum.md — Owner-Approved Exercise Baseline (2026-10-10); EXA-001/002/004/005/008/010/011/012/013/015/016; Numerical Targets and Attribution (historical accepted exercise assumptions)
docs/case_study_48_addendum.md — Subsequent Application Exercise Builds (2026-10-11); Current Learning and Parallel Experiment (owner direction; feasibility not benefit)
docs/adrs/0001-azure-architecture.md — Exercise Applicability (2026-10-11); Decisions; Hybrid M365 and Excel transition; Options still to compare (proposed)
docs/ideas/typesafe-system-one-agent-fit.md — Observed Feasibility and Parallel Value Experiment (2026-10-11); Microsoft Decision 1 Reassessment (2026-10-10). PR #58 pinned 5136f192d583a5bf53adeeec4b0f21369b005c9d; inspected in maintained documentation 2026-10-11, not runtime reverified

## Slide 20
APPENDIX C • REVIEW AND PROVENANCE
Read the evidence label before reading the claim
20 / PROPER WARM • AS AT 11 Oct 2026 • REPOSITORY-ONLY • NO NEW LEGAL CURRENTNESS CHECK
REQUEST / RESEARCH
Original ambition is not an outcome.
Sector patterns are not company facts.
Role instruments are not interviews.
EXERCISE / DIRECTION
Fictional fixtures are not budgets.
Accepted v0.12 is historical.
v0.13 is pending fresh review.
PROPOSED / OBSERVED
Target topology is not deployed proof.
Pinned feasibility is narrow.
Benefit and readiness are unproved.
Full source/date/status in notes • Independent findings addressed • Timed rehearsal pending
Notes: Evidence categories: REQUEST is the immutable case ambition; RESEARCH is sector evidence or role-agent hypothesis; EXERCISE is a selected fictional fixture or historical owner-approved baseline; DIRECTION is the current owner's delivery requirement; PROPOSED is design or evaluation not yet accepted; OBSERVED FEASIBILITY is a precisely pinned recorded service result; UNPROVED is benefit or readiness still lacking evidence.
All consequential legal adoption requires fresh official-source verification and professional/control-owner approval. v0.12 acceptance on 10 October does not transfer to v0.13. PR #58 evidence is pinned at 5136f192d583a5bf53adeeec4b0f21369b005c9d in maintained main documentation, not imported source or a re-inspected runtime.
The full capstone guide informed the narrative. A deck cannot establish live delivery, Q&A behaviour, working autonomy, operations or publication floors. Independent strategist findings are recorded in the tracking review and addressed in this build; a timed rehearsal remains pending. Detailed source/provision/date/status references are in notes and research/evidence-register.md.
Evidence:
docs/case_study_48_original.md — Business Challenge; Agentic Architecture Brief; Expected Outcomes (2026-09-10, immutable request)
docs/reference/research/company/agent-request-challenge.md — Purpose and Method; Summary (2026-09-26, role-agent hypotheses)
docs/case_study_48_addendum.md — Owner-Approved Exercise Baseline (2026-10-10); EXA-001/002/004/005/008/010/011/012/013/015/016; Numerical Targets and Attribution (historical accepted exercise assumptions)
docs/case_study_48_addendum.md — Subsequent Application Exercise Builds (2026-10-11); Current Learning and Parallel Experiment (owner direction; feasibility not benefit)
docs/prds/proper-warm-retrofit-programme-demonstrator.md — front matter; Executive Summary; CON-009/AC-057 (v0.13.0 candidate 2026-10-11; historical v0.12.0 accepted 2026-10-10)
docs/ideas/typesafe-system-one-agent-fit.md — Observed Feasibility and Parallel Value Experiment (2026-10-11); Microsoft Decision 1 Reassessment (2026-10-10). PR #58 pinned 5136f192d583a5bf53adeeec4b0f21369b005c9d; inspected in maintained documentation 2026-10-11, not runtime reverified
docs/reference/method/ama-capstone-assessment-guide.md — Sections A-D; How the outcome is determined; How to prepare (2026-09-30 published rubric)

## Slide 21
APPENDIX D • OPTIONS GATE • NO WINNER SCORED
Compare the routes before selecting a winner
Decision criterion | Excel-only improvement | M365 / business platform | Azure-led hybrid
Workflow / evidence | Workbook stays; fit unverified | Greenfield Power Apps / Dataverse | Shared API; proposed
Permissions | Controls / roles unverified | Roles proposed; tenant fit unverified | Server API checks; proof needed
Migration | Less change possible; fit unverified | Greenfield; migration unverified | Staged import; exit test
Integration | Workbook / API links unverified | Connectors / sources unverified | API / source links proposed
Resident access | Non-digital required; untested | Non-digital required; untested | Non-digital required; untested
Whole-life cost | Not assessed | Licence / support unverified | Run cost not assessed
Readiness | Baseline / controls unverified | Tenant check needed | Exercise direction only
No common-basis cost or fit evidence yet. Compare controls, tenant, migration and support before choice.
21 / PROPER WARM • QUALITATIVE DESIGN HYPOTHESES • ADR 0001 • OQ-012
Notes: This is a comparison framework, not a scored recommendation. Excel-only improvement may minimize change, but control fit and the manual baseline still need evidence. The greenfield Power Apps/Dataverse business-platform option and Azure-led hybrid both need fair, equal-scope appraisal. Tenant fit, licences, workflows and resident access have not been tested. The Azure-led hybrid is the exercise direction for connected workflows and real AI, SQL and Azure evidence; it is not a production decision and costs are not measured.
Ask owners to compare the routes on the same workload, controls, transition risk, accessibility, integration, support and whole-life cost. Identify tenant capability, workbook quality, baseline effort and failure fallback. Score only when comparable evidence exists; mandatory safety, privacy, resident and approval controls are gates, not tradeable points.
Evidence:
docs/adrs/0001-azure-architecture.md — Hybrid M365 and Excel transition; Options still to compare; Provisional options appraisal (architect illustration is not an approved decision)
docs/case_study_48_addendum.md — Implementation Options and Provisional Platform Recommendation; EXA-012 / OQ-012
docs/case_study_48_original.md — Business Challenge (spreadsheets stated; specific workbook failure modes not measured)