## Slide 1
ZAVA NORTH HOMES
Zava Forward
A governed retrofit delivery service that turns evidence and investment into safe, resident-accepted outcomes
DECISION REQUESTED
Approve a capped 6-8 week readiness stage
NOT REQUESTED TODAY
Portfolio rollout, capital acceleration or a five-agent build
CxO initial proposal | 18 September 2026
Notes: Open from a fixed position: "The outcome we need today is a bounded
decision." We are asking to fund evidence, not assume scale. Approval does
not authorise AI deployment, resident contact, works instructions, capital
acceleration or grant recognition. Pause after stating what is not requested.

## Slide 2
The delivery challenge is credible; its binding cause is not yet known
KNOWN
60,000 homes
Small spreadsheet-led team
Delivery described as behind plan
POSSIBLE CONSTRAINTS
Data quality
Capital and cash
Competent capacity
Supplier capacity
Property complexity
Resident access
Quality failure
Grant conditions
EXECUTIVE RISK
Automating the wrong constraint makes activity faster - not outcomes better.
Success means an accepted handover, not a task completed.
Evidence status: case-study facts + company unknowns + risk hypothesis
Notes: Avoid criticising the current team or spreadsheets. Spreadsheet dependency
signals fragmented coordination, but it does not prove administration is the
binding constraint. Define delivery as a safe, resident-accepted,
evidence-complete handover. Readiness must identify which constraints
materially limit that outcome.

## Slide 3
Current duties and funding milestones create a decision window
27 OCT 2025
Awaab's Law Phase 1 in force
30 NOV 2026
Phase 2 due; reconfirm applicability
31 MAR 2028
WH:SHF grant spend deadline recorded
2030
EPC C remains a proposal in the case materials
VERIFY AT EACH APPROVAL GATE
Notes: Urgency does not remove the need to diagnose the constraint. Existing hazard
services and eligible grant delivery cannot wait for a new platform. Do not
describe EPC C by 2030 as an in-force statutory deadline or imply that a
Zava North Homes grant allocation is confirmed. Regulatory applicability
must be checked at each consequential decision.

## Slide 4
One governed property journey across existing services
IDENTIFY
ASSESS
AGREE
FUND
SCHEDULE
INSTALL
ASSURE
HANDOVER
One visible lifecycle | Separate safety, resident, professional, supplier, funding and quality gates
ASSET
SYSTEM
REPAIRS
SYSTEM
HOUSING
SYSTEM
FINANCE
SYSTEM
CONTRACTOR
SYSTEMS
SHARED WORKFLOW + EVIDENCE LAYER - CONNECT, DO NOT REPLACE
Notes: Make the future state tangible: every executive question should trace to the
same property evidence, decision, owner and exception. The control plane
connects existing services; it does not replace every system. Emergency,
damp-and-mould, safeguarding, complaints and repairs routes remain
independently available and take precedence.

## Slide 5
Automation handles evidence; people retain consequential authority
THE SERVICE MAY
Recommend priorities
Reconcile records and flag conflicts
Pre-populate sourced facts
Draft resident, grant and management packs
Suggest schedules within confirmed constraints
Check evidence and flag anomalies
THE SERVICE MUST NOT
Diagnose hazards
Release a safety hold
Approve PAS 2035 outputs
Infer resident consent
Commit capital or award work
Submit claims, accept quality or close defects
Deterministic workflow enforces the gate. An authorised person makes the controlled decision.
Notes: Use the exact verbs recommend, draft, reconcile and flag. Competent
professionals own PAS 2035 outputs. Residents retain measure-specific
decisions. Finance, safety, procurement and quality authorities retain their
mandates. Resident silence, survey access or an accepted appointment must
never be interpreted as installation consent.

## Slide 6
The programme earns the right to progress at each decision gate
1 READINESS | 6-8 WEEKS
Establish the baseline, binding constraint and viable options.
2 SHADOW MODE
Test recommendations and drafts with no live consequences.
3 CONTROLLED PILOT | 6-9 MONTHS
Operate one bounded delivery cell under explicit controls.
4 TRANCHE DECISIONS
Repeat or scale only where evidence supports it.
EVERY GATE CAN DECIDE
PROCEED
REDESIGN
SELECT A NON-AGENTIC OPTION
PAUSE OR STOP
Sequence of decisions, not a commitment to scale
Notes: This is not a phased commitment to scale. Each stage releases only the
authority and expenditure justified by evidence. A successful readiness
stage may recommend conventional process redesign or rules-based workflow.
The proposed pilot size and duration remain subject to readiness validation.

## Slide 7
Readiness will answer whether, where and how to pilot
BASELINE
Property and building data
Throughput and delay causes
RESIDENT
Journeys and accessibility
Exceptions and redress
CAPACITY
PAS 2035 competence
Supplier route and contingency
FINANCE
Grant and funding status
Headroom and downside
OPTIONS APPRAISAL
Process and existing platform
Rules-based workflow or bounded AI
CONTROL OWNERS
Safety, resident, finance and procurement
Data, digital and professional roles
PILOT BUSINESS CASE + CONTROL PACK
Notes: Answer the executive question: what are we buying in eight weeks? Each
output needs a named owner. Require a twelve-month baseline by property
archetype, measure, supplier and lifecycle stage, including reopened work.
If coordination is not a material constraint, do not force an agentic
solution.

## Slide 8
The pilot tests outcomes, controls and incremental value together
1 SAFETY + PROFESSIONAL AUTHORITY
2 RESIDENT DECISIONS + EXPERIENCE
3 QUALITY + EVIDENCE COMPLETENESS
4 ACCEPTED THROUGHPUT + EFFORT
5 SUPPLIER + COMPETENT CAPACITY
6 COST + GRANT + PEAK CASH
7 BOUNDED AI VALUE VS CONVENTIONAL OR RULES-BASED WORKFLOW
Control conditions: zero unauthorised starts | zero autonomous controlled approvals | no missed critical exception in agreed tests
Notes: A pilot passes only if it improves accepted outcomes without weakening
safety, resident rights, quality or affordability. Proposed cycle-time and
administration targets are unratified until readiness. Keep absolute
exceptions visible. A small pilot cannot prove universal safety or seasonal
energy and affordability outcomes.

## Slide 9
The value case is conversion and control - not gross programme value
VALUE HYPOTHESES
Fewer avoidable delays and repeat work
Better grant claim and cash conversion
Better alignment of retrofit and maintenance
Clearer capital and downside exposure
Stronger resident, Board and audit evidence
NOT YET PROVEN
Doubled delivery
GBP 40m secured grant
Hundreds of millions protected borrowing capacity
Universal resident bill reductions
ATTRIBUTABLE BENEFIT - DATA - INTEGRATION - PEOPLE - REVIEW - ASSURANCE - SUPPORT - EXIT
Notes: Technology value must be incremental to the underlying retrofit plan and
exceed its full operating and assurance burden. Staff time released is
capacity, not a cash saving unless expenditure changes. Existing-plan grant
is not an incremental benefit. Measure resident comfort, affordability and
bill effects separately.

## Slide 10
The scenarios justify readiness, not an investment commitment
Illustrative scenario | Result | Evidence status
26% of 60,000 homes below EPC C | 15,600 | Sector-derived planning cohort
15,600 homes over four years | 3,900 / year | Derived accepted-completion trajectory
15,600 x GBP 20,000 | GBP 312m | Planning assumption, not a budget
GBP 7,500 ordinary grant cap x 15,600 | GBP 117m | Maximum-ceiling illustration, not an award
GBP 40m at the cap | ~5,333 homes | Rounded scenario, not secured funding
ILLUSTRATIVE - NOT A COMPANY FORECAST
Notes: Use the numbers to make one point: even the scenario implies material
provider funding and delivery exposure. Do not present the 74% EPC C sector
estimate as the Zava North Homes baseline. Finance must validate eligible
homes, award status, cost inclusions, match funding, peak cash, covenant
headroom and downside tolerances.

## Slide 11
Approve the bounded next step
APPROVE NOW
Phase 0 purpose and 6-8 week timetable
Finance-approved cost ceiling
Named sponsor and control owners
Readiness evidence pack and return date
Conditional pilot reservation
DO NOT RELEASE YET
Live consequential automation
Resident contact through the new service
Works instruction or capital acceleration
Grant recognition or procurement commitment
Portfolio rollout
RETURN WITH: PROCEED TO SHADOW MODE | REDESIGN | SELECT NON-AGENTIC OPTION | STOP
Controlled momentum. Capped exposure. Evidence before scale.
Notes: Return to direct decision language. "The need to improve delivery is
credible. The case for a five-agent rollout is not yet proven. Approve the
capped readiness stage and conditional pilot pathway so we can return with
evidence and a controlled go, redesign or stop decision." Ask each control
owner whether the resolution preserves their authority, then stop speaking.